## Sheet1
Module | User Story | Task | Estimaed Point | Assign To | Start Date | Complete Date | Consumed Point | Remarks
Campus & Depatment Management | Create and Manage Campuses | Frontend Tasks: | 2
|  | Design a form for creating and editing campus details. | 1
|  | Develop a campus list view with search and filter functionalities. | 0.5
|  | Implement a details view for displaying campus information. | 0.2
|  | Integrate functionality for deleting campuses with confirmation dialogs. | 0.2
|  | Create user-friendly error messages and validation for data inputs. | 0.1
|  | Backend Tasks: | 2
|  | Implement REST API endpoints for CRUD operations on campuses (Create, Read, Update, Delete). | 1
|  | Implement data validation and error handling in API. | 0.6
|  | Ensure that deletion of campuses checks for dependencies, such as linked departments. | 0.2
|  | Develop service methods for managing campus data logic. | 0.2
| Create and Manage Departments | Frontend Tasks: | 2
|  | Design a form for creating and editing department details. | 1
|  | Develop a department list view with options to filter by campus. | 0.5
|  | Implement a details view for displaying department information. | 0.2
|  | Create a delete confirmation dialog for department removal. | 0.2
|  | Provide user-friendly validation and error messaging for department data inputs. | 0.1
|  | Backend Tasks: | 2
|  | Implement REST API endpoints for CRUD operations on departments. | 1
|  | Ensure validation and error handling are present for API operations. | 0.6
|  | Ensure departments are linked to valid campuses and check dependencies on deletion. | 0.2
|  | Develop service methods to handle department logic. | 0.2
User Access Management | Manage User Roles | Frontend Tasks: | 2
|  | Design a user-friendly interface for creating and editing user roles. | 1
|  | Develop a role list view with sorting and filtering capabilities. | 0.5
|  | Implement functionality to view role details. | 0.2
|  | Integrate role deletion with confirmation dialogs. | 0.2
|  | Ensure proper validation and display of error messages. | 0.1
|  | Backend Tasks: | 2
|  | Implement REST API endpoints for CRUD operations on user roles. | 1
|  | Handle data validation and error checking in API methods. | 0.6
|  | Implement logic to prevent deletion of roles linked to active users. | 0.2
|  | Develop service methods to manage role-related business logic. | 0.2
| Manage Users | Frontend Tasks: | 2
|  | Design a form for user creation and editing, including password management. | 1
|  | Develop a user list view with sorting and filtering options. | 0.5
|  | Implement user detail view to display account information. | 0.2
|  | Integrate user deletion and status activation/deactivation. | 0.2
|  | Provide validation and user feedback mechanisms. | 0.1
|  | Backend Tasks: | 2
|  | Implement REST API endpoints for user account management. | 1
|  | Include password hashing and security checks. | 0.6
|  | Ensure role assignment functionality and handle validation. | 0.2
|  | Implement logic to manage user activation status. | 0.2
| Configure User Permissions | Frontend Tasks: | 1.4
|  | Design an interface for configuring permissions by role and entity. | 0.5
|  | Develop a list view for existing permissions with sorting/filtering options. | 0.5
|  | Implement functionality to edit permissions for each role. | 0.2
|  | Provide validation and feedback for permission settings. | 0.2
|  | Backend Tasks: | 2
|  | Implement REST API endpoints for managing permissions. | 0.5
|  | Handle validation for permissions to ensure logical consistency. | 0.6
|  | Implement logic to apply permission changes system-wide. | 0.7
|  | Develop service methods for permissions-related operations. | 0.2
Classes & Section Management | Manage Classrooms | Frontend Tasks: | 2
|  | Design a user interface for creating and editing classroom information. | 1
|  | Develop a list view with sorting and filtering capabilities for viewing classrooms. | 0.5
|  | Implement functionality to view classroom details. | 0.2
|  | Provide validation for capacity and other fields. | 0.2
|  | Integrate confirmation dialogs for deletion. | 0.1
|  | Backend Tasks: | 2
|  | Implement API endpoints for CRUD operations on classrooms. | 0.5
|  | Validate inputs and ensure logical consistency (e.g., capacity cannot be negative). | 0.6
|  | Implement business logic for classroom management. | 0.7
|  | Handle authentication and authorization for classroom management. | 0.2
| Manage Classes | Frontend Tasks: | 1.5
|  | Design interfaces for creating and editing class information. | 0.5
|  | Develop a class list view with sorting and filtering options. | 0.5
|  | Implement functionality to view class details. | 0.3
|  | Integrate class deletion with proper validation and confirmation. | 0.2
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing classes. | 0.7
|  | Handle data validation and consistency checks. | 0.5
|  | Ensure unique class names and handle duplicate checks. | 0.2
|  | Develop services for class-related business logic. | 0.6
| Manage Sections | Frontend Tasks: | 1.5
|  | Design interfaces for creating and editing section information. | 0.5
|  | Develop a class list view with sorting and filtering options. | 0.5
|  | Implement functionality to view class details. | 0.3
|  | Integrate class deletion with proper validation and confirmation. | 0.2
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing sections. | 0.7
|  | Handle data validation and consistency checks. | 0.5
|  | Ensure unique class names and handle duplicate checks. | 0.2
|  | Develop services for class-related business logic. | 0.6
| Assign Classrooms to Classes | Frontend Tasks: | 1.5
|  | Design interfaces for assigning classrooms to classes and sections. | 0.7
|  | Implement a view for current assignments with filtering and sorting. | 0.5
|  | Provide validation for ensuring assignments respect capacity limits. | 0.3
|  | Backend Tasks: | 2.5
|  | Implement API endpoints for managing classroom assignments. | 0.7
|  | Validate assignments to ensure they meet capacity and availability criteria. | 0.5
|  | Develop logic for handling assignment conflicts and resolutions. | 0.3
Admission Management | Manage Applicants | Frontend Tasks: | 2.2
|  | Design a form for entering applicant details. | 1
|  | Implement a list view for applicants with sorting and filtering options. | 0.5
|  | Develop an interface to update and view applicant details. | 0.5
|  | Ensure form validation for fields like email, phone number, and date of birth. | 0.2
|  | Backend Tasks: | 2.5
|  | Implement API endpoints for creating, updating, and retrieving applicant information. | 1
|  | Validate applicant data to ensure integrity (e.g., unique email address). | 0.5
|  | Implement authentication and authorization for managing applicants. | 0.5
| Manage Applications | Frontend Tasks: | 1
|  | Design a view to display and manage application statuses. | 0.5
|  | Implement functionality to update application decisions (e.g., approve, reject). | 0.3
|  | Allow filtering of applications by status and campus. | 0.2
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing applications and their statuses. | 0.5
|  | Validate application status transitions. | 0.2
|  | Implement business logic for processing applications. | 0.3
| Manage Admissions & Student Enrolment | Frontend Tasks: | 2
|  | Design an interface for enrolling students and managing admissions. | 1
|  | Implement a view to list admissions with filters by class and section. | 0.7
|  | Allow updates to admission records, such as changing sections. | 0.3
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing admissions. | 1
|  | Validate admission data, ensuring unique mapping of students and applications. | 0.5
|  | Handle business logic for enrolling students and assigning sections. | 0.5
Student Academic Management | Track Student Academics | Frontend Tasks: | 2
|  | Design a view for managing student academic records. | 1
|  | Implement functionality to promote students and update their records. | 0.5
|  | Provide a timeline view of student academic history. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing student academics. | 1
|  | Validate promotion logic and academic year consistency. | 0.5
|  | Handle business logic for academic records, ensuring data integrity. | 0.5
| Manage Student Attendance | Frontend Tasks: | 2
|  | Design an attendance-taking interface for teachers. | 1
|  | Implement views to display attendance records by class and date. | 0.5
|  | Provide functionality to update and correct attendance records. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for recording and retrieving attendance. | 1
|  | Validate attendance data, ensuring accuracy and completeness. | 0.5
|  | Handle business logic for attendance tracking and reporting. | 0.5
Employee Management | Manage Employee Roles | Frontend Tasks: | 2.2
|  | Design a form for entering role details. | 1
|  | Implement a list view for roles with sorting and filtering options. | 0.5
|  | Develop an interface to update and view role details. | 0.5
|  | Ensure form validation for unique role names. | 0.2
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving roles. | 1
|  | Validate role data to ensure uniqueness and integrity. | 0.5
|  | Implement authentication and authorization for role management. | 0.5
| Manage Employees / Profiling | Frontend Tasks: | 2.2
|  | Design a form for entering employee details. | 1
|  | Implement a list view for employees with sorting and filtering options. | 0.5
|  | Develop an interface to update and view employee details. | 0.5
|  | Ensure form validation for fields like email and phone number. | 0.2
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving employee information. | 1
|  | Validate employee data to ensure integrity and uniqueness (e.g., unique email addresses). | 0.5
|  | Implement business logic for role and department assignments. | 0.5
| Manage Employee Attendance | Frontend Tasks: | 2.5
|  | Design an attendance-taking interface for employees. | 1.5
|  | Implement views to display attendance records by date. | 0.5
|  | Provide functionality to update and correct attendance records. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for recording and retrieving attendance. | 1
|  | Validate attendance data, ensuring accuracy and completeness. | 0.5
|  | Handle business logic for attendance tracking and reporting. | 0.5
| Manage Employee Leaves | Frontend Tasks: | 2
|  | Design an interface for submitting and viewing leave requests. | 1
|  | Implement functionality to approve or reject leave requests. | 0.5
|  | Provide views to filter and search leave records by employee and status. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing leave requests and statuses. | 1
|  | Validate leave data to ensure logical consistency. | 0.5
|  | Handle business logic for leave approval workflows. | 0.5
| Manage Performance Appraisals | Frontend Tasks: | 2
|  | Design a form for entering appraisal details and scores. | 1
|  | Implement a view for displaying and filtering appraisal records. | 0.5
|  | Provide functionality to update and view appraisal comments and scores. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing appraisals. | 1
|  | Validate appraisal data to ensure accuracy and completeness. | 0.5
|  | Handle business logic for performance evaluation processes. | 0.5
| Manage Employee Trainings | Frontend Tasks: | 2
|  | Design a form for entering training details and certifications. | 1
|  | Implement a view for displaying and filtering training records. | 0.5
|  | Provide functionality to update and view training participation and results. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing training records. | 1
|  | Validate training data to ensure accuracy and completeness. | 0.5
|  | Handle business logic for training participation and certification processes. | 0.5
| Manage Employee Benefits | Frontend Tasks: | 2
|  | Design a form for entering benefit details and assignments. | 1
|  | Implement a view for displaying and filtering benefit records. | 0.5
|  | Provide functionality to update and view benefit details and assignments. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for managing benefit records. | 1
|  | Validate benefit data to ensure accuracy and completeness. | 0.5
|  | Handle business logic for benefit assignment and tracking processes. | 0.5
Payroll Management | Manage Employee Allowances | Frontend Tasks: | 2
|  | Design a form for entering and updating allowance details. | 1
|  | Implement a list view for allowances with sorting and filtering options by employee, type, and month. | 0.5
|  | Develop an interface to view allowance details for each employee. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving allowance data. | 1
|  | Validate allowance data to ensure completeness and logical consistency. | 0.5
|  | Handle business logic for calculating total allowances for payroll integration. | 0.5
| Manage Employee Bonuses | Frontend Tasks: | 2
|  | Design a form for entering and updating bonus details. | 1
|  | Implement a list view for bonuses with sorting and filtering options by employee, type, and month. | 0.5
|  | Develop an interface to view bonus details for each employee. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving bonus data. | 1
|  | Validate bonus data to ensure completeness and logical consistency. | 0.5
|  | Handle business logic for calculating total bonuses for payroll integration. | 0.5
| Manage Employee Payroll | Frontend Tasks: | 3.5
|  | Design a form for entering payroll details and calculations. | 2
|  | Implement a view for displaying and filtering payroll records by employee and month. | 1
|  | Develop functionality to update and finalize payroll calculations. | 0.5
|  | Backend Tasks: | 4
|  | Implement API endpoints for creating, updating, and retrieving payroll data. | 2
|  | Validate payroll data to ensure accuracy and completeness. | 1
|  | Handle business logic for calculating net pay based on salary, allowances, bonuses, and deductions. | 1
Subject Management & Course | Manage Subjects | Frontend Tasks: | 2
|  | Design a form for adding and editing subject details. | 1
|  | Implement a list view to display all subjects with options to filter and search. | 0.5
|  | Develop an interface to view detailed information about each subject. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving subject data. | 1
|  | Validate subject data to ensure uniqueness and completeness. | 0.5
|  | Handle business logic for activating and deactivating subjects. | 0.5
| Assign Subjects to Classes | Frontend Tasks: | 2
|  | Design a form for assigning subjects to classes. | 1
|  | Implement a view to display assigned subjects for each class. | 0.5
|  | Develop functionality to update and remove subject assignments. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving class subject assignments. | 1
|  | Validate assignments to ensure subjects are unique within a class. | 0.5
|  | Handle business logic for managing subject assignments. | 0.5
| Manage Subject Teachers | Frontend Tasks: | 1.5
|  | Design a form for assigning teachers to subjects. | 0.5
|  | Implement a view to display assigned teachers and their roles for each subject. | 0.5
|  | Develop functionality to update and remove teacher assignments. | 0.5
|  | Backend Tasks: | 1.5
|  | Implement API endpoints for creating, updating, and retrieving subject teacher assignments. | 0.5
|  | Validate assignments to ensure correct role designation. | 0.5
|  | Handle business logic for managing teacher assignments. | 0.5
| Manage Timetables | Frontend Tasks: | 2.5
|  | Design a form for scheduling subjects in timetables. | 1
|  | Implement a view to display and edit timetable entries. | 1
|  | Develop functionality to resolve scheduling conflicts. | 0.5
|  | Backend Tasks: | 2
|  | Implement API endpoints for creating, updating, and retrieving timetable data. | 0.5
|  | Validate timetable entries to prevent conflicts in scheduling. | 0.5
|  | Handle business logic for managing timetable entries. | 1
Exam Management | Manage Exams | Frontend Tasks: | 5
|  | Design a form for scheduling exams with fields for date, time, location, and type. | 2
|  | Implement a calendar view to display all scheduled exams. | 2
|  | Develop functionality to update and cancel exams. | 1
|  | Backend Tasks: | 4
|  | Implement API endpoints for creating, updating, retrieving, and deleting exams. | 2
|  | Validate exam data to ensure scheduling conflicts are avoided. | 1
|  | Handle business logic for activating and deactivating exams. | 1
| Manage Exam Results | Frontend Tasks: | 4
|  | Design a form for entering and updating student exam scores. | 1
|  | Implement a view to display exam results for individual students and classes. | 1
|  | Develop functionality to analyze and report on student performance. | 2
|  | Backend Tasks: | 3
|  | Implement API endpoints for creating, updating, retrieving, and deleting exam results. | 1
|  | Validate exam results to ensure data integrity. | 1
|  | Handle business logic for activating and deactivating exam results. | 1
| Manage Grades | Frontend Tasks: | 1.5
|  | Design a form for awarding grades to students. | 0.5
|  | Implement a view to display student grades by subject and class. | 0.5
|  | Develop functionality to update and analyze student grades. | 0.5
|  | Backend Tasks: | 2.5
|  | Implement API endpoints for creating, updating, retrieving, and deleting grades. | 1
|  | Validate grade data to ensure consistency and accuracy. | 0.5
|  | Handle business logic for managing grade entries. | 1
| Generate and Manage Transcripts | Frontend Tasks: | 3
|  | Design a form for generating transcripts with options for including specific academic records. | 2
|  | Implement a view to display and download student transcripts. | 0.5
|  | Develop functionality to update and archive transcripts. | 0.5
|  | Backend Tasks: | 2.5
|  | Implement API endpoints for generating, retrieving, updating, and deleting transcripts. | 1
|  | Validate transcript data to ensure accuracy and completeness. | 0.5
|  | Handle business logic for managing transcript records. | 1
Sponsorship Management | Manage Sponsors / Profiling | Frontend Tasks | 2.5
|  | Create a form to add new sponsors. | 1
|  | Create a list to display all sponsors with details (name, email, phone, address, status). | 0.5
|  | Implement search and filter functionalities for sponsors. | 0.5
|  | Implement edit and delete functionalities for sponsors. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoints for adding, updating, deleting, and retrieving sponsors. | 1
|  | Implement business logic for sponsor validation (e.g., unique email). | 0.5
|  | Implement soft delete for sponsors (update IsActive flag instead of deleting). | 0.5
| Manage Sponsorship | Frontend Tasks | 3
|  | Create a form to create new sponsorships. | 1
|  | Create a list to display all sponsorships with details (sponsor, student, amount, schedule, status). | 1
|  | Implement search and filter functionalities for sponsorships. | 0.5
|  | Implement edit and delete functionalities for sponsorships. | 0.5
|  | Backend Tasks | 2.5
|  | Create API endpoints for adding, updating, deleting, and retrieving sponsorships. | 1
|  | Implement business logic for sponsorship validation (e.g., amount, schedule). | 1
|  | Implement soft delete for sponsorships (update IsActive flag instead of deleting). | 0.5
| Manage Sponsor Payments | Frontend Tasks | 4
|  | Create a list to display all sponsor payments with details (sponsorship, payment date, amount, method). | 1
|  | Implement search and filter functionalities for payments. | 1
|  | Generate payment reports (e.g., total payments by sponsor, payment summary). | 2
|  | Backend Tasks | 2
|  | Create API endpoints for retrieving sponsor payments. | 1
|  | Implement business logic for calculating payment totals and generating reports. | 1
Fee Management | Manage Fee Categories | Frontend Tasks | 3
|  | Create a form to add new fee categories. | 1
|  | Create a list to display all fee categories with details (name, description, status). | 1
|  | Implement search and filter functionalities for fee categories. | 0.5
|  | Implement edit and delete functionalities for fee categories. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoints for adding, updating, deleting, and retrieving fee categories. | 1
|  | Implement business logic for fee category validation. | 0.7
|  | Implement soft delete for fee categories (update IsActive flag instead of deleting). | 0.3
| Manage Class Fees | Frontend Tasks | 3
|  | Create a form to add fees for a class. | 1
|  | Create a list to display fees for each class with details (class, fee category, amount, campus). | 1
|  | Implement search and filter functionalities for class fees. | 0.5
|  | Implement edit and delete functionalities for class fees. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoints for adding, updating, deleting, and retrieving class fees. | 1
|  | Implement business logic for class fee validation (e.g., unique fee category per class). | 0.7
|  | Implement soft delete for class fees (update IsActive flag instead of deleting). | 0.3
| Manage Student Fees | Frontend Tasks | 1.5
|  | Assign fees to students based on their class and campus. | 0.5
|  | Apply discounts and sponsorships to student fees. | 0.5
|  | View a list of students with their assigned fees and due amounts. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoints for assigning fees, applying discounts, and retrieving student fees. | 1
|  | Implement business logic for calculating student fees based on class fees and discounts. | 1
| Generate and Manage Fee Vouchers | Frontend Tasks | 2.5
|  | Generate fee vouchers for students based on their assigned fees. | 1
|  | View and manage fee vouchers (due date, paid status, payments, adjustments). | 0.5
|  | Generate fee reports (e.g., outstanding fees, payment summaries). | 1
|  | Backend Tasks | 2.5
|  | Create API endpoints for generating fee vouchers, retrieving voucher details, and generating reports. | 1.5
|  | Implement business logic for calculating voucher totals and due dates. | 1
| Manage Fee Payments and Adjustments | Frontend Tasks | 2
|  | Record fee payments against vouchers. | 1
|  | Make adjustments to fee vouchers (e.g., waivers, penalties). | 0.5
|  | View payment history and adjustment details. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoints for recording payments and adjustments. | 1
|  | Implement business logic for updating voucher status and calculating balances. | 1
Parent Management | Manage Parent Information | Frontend Tasks | 2
|  | Create a form to add new parents. | 0.5
|  | Create a list to display all parents with details (name, email, phone, address, status). | 0.5
|  | Implement search and filter functionalities for parents. | 0.5
|  | Implement edit and delete functionalities for parents. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoints for adding, updating, deleting, and retrieving parents. | 1
|  | Implement business logic for parent validation (e.g., unique email). | 0.5
|  | Implement soft delete for parents (update IsActive flag instead of deleting). | 0.5
| Manage Parent-Student Relationships | Frontend Tasks | 1.5
|  | Assign parents to students and vice versa. | 0.5
|  | View parent-student relationships. | 0.7
|  | Remove parent-student relationships. | 0.3
|  | Backend Tasks | 1.5
|  | Create API endpoints for creating, updating, and deleting parent-student relationships. | 1
|  | Implement business logic for validating parent-student relationships. | 0.5
| Submit Feedback | Frontend Tasks | 1
|  | Create a form for parents to submit feedback for their children. | 0.5
|  | Display a list of submitted feedback for parents to view. | 0.5
|  | Backend Tasks | 2
|  | Create API endpoint for submitting parent feedback. | 0.5
|  | Implement business logic for storing and retrieving parent feedback. | 0.5
Notification Management | Send Notifications to Users | Frontend Tasks | 1.5
|  | Create a form to compose notifications. | 1
|  | Select user type and target users. | 0.2
|  | Choose notification delivery method (email, SMS). | 0.1
|  | View a list of sent notifications with details (user type, message, date sent, sent via). | 0.2
|  | Backend Tasks | 2.5
|  | Create API endpoints for sending notifications. | 1
|  | Implement logic to send notifications based on user type and delivery method. | 0.5
|  | Store notification details in the Notifications table. | 0.5
|  | Log email details in the EmailLogs table for email notifications. | 0.5
| View Notifications | Frontend Tasks | 1
|  | Display a list of notifications for the logged-in user. | 0.5
|  | Mark notifications as read. | 0.5
|  | Backend Tasks | 1.5
|  | Create API endpoints to retrieve user notifications. | 0.5
|  | Implement logic to update notification status as read. | 0.5
| View Email Logs | Frontend Tasks | 1
|  | Display a list of sent emails with details (recipient, subject, date sent). | 0.5
|  | Search and filter email logs. | 0.5
|  | Backend Tasks | 1.5
|  | Create API endpoints to retrieve email logs. | 0.5
|  | Implement search and filter functionality for email logs. | 0.5
Financial Accounting Management | Manage Fiscal Years | Frontend Tasks | 2
|  | Create a form to add new fiscal years. | 0.5
|  | Create a list to display all fiscal years with details (start date, end date, status). | 0.5
|  | Implement search and filter functionalities for fiscal years. | 0.5
|  | Implement edit and delete functionalities for fiscal years. | 0.5
|  | Backend Tasks | 1.5
|  | Create API endpoints for adding, updating, deleting, and retrieving fiscal years. | 0.5
|  | Implement business logic for fiscal year validation (e.g., non-overlapping dates). | 0.5
|  | Implement soft delete for fiscal years (update IsActive flag instead of deleting). | 0.5
| Manage Ledger Accounts | Frontend Tasks | 3
|  | Create a form to add new ledger accounts. | 1
|  | Create a hierarchical view of ledger accounts (chart of accounts). | 1
|  | Implement search and filter functionalities for ledger accounts. | 0.5
|  | Implement edit and delete functionalities for ledger accounts. | 0.5
|  | Backend Tasks | 3.5
|  | Create API endpoints for adding, updating, deleting, and retrieving ledger accounts. | 1
|  | Implement business logic for account validation (e.g., unique account code). | 1
|  | Implement hierarchical structure for ledger accounts. | 1
|  | Implement soft delete for ledger accounts (update IsActive flag instead of deleting). | 0.5
| Create Journal Entries | Frontend Tasks | 3.5
|  | Create a form to create journal entries with debit and credit details. | 1.5
|  | View a list of journal entries with details (date, description, posted status). | 1
|  | Implement search and filter functionalities for journal entries. | 0.5
|  | Implement posting and reversing journal entries. | 0.5
|  | Backend Tasks | 3
|  | Create API endpoints for creating, updating, deleting, and retrieving journal entries. | 1
|  | Implement business logic for journal entry validation (e.g., debit equals credit). | 1
|  | Implement posting and reversing journal entries logic. | 0.5
|  | Update account balances based on journal entries. | 0.5
| Manage Vouchers | Frontend Tasks | 3
|  | Create forms for different voucher types (payment, receipt, journal). | 1
|  | View a list of vouchers with details (type, number, date, description). | 1
|  | Implement search and filter functionalities for vouchers. | 0.5
|  | Implement voucher approval and cancellation. | 0.5
|  | Backend Tasks | 3.5
|  | Create API endpoints for creating, updating, deleting, and retrieving vouchers. | 1
|  | Implement business logic for voucher validation. | 1
|  | Implement voucher approval and cancellation workflows. | 1
|  | Update account balances based on voucher entries. | 0.5
| Manage Budgets | Frontend Tasks | 3
|  | Create a form to create budgets for different accounts and periods. | 1
|  | View budget details and comparisons to actual spending. | 1
|  | Implement search and filter functionalities for budgets. | 0.5
|  | Implement budget adjustments. | 0.5
|  | Backend Tasks | 3
|  | Create API endpoints for creating, updating, deleting, and retrieving budgets. | 1
|  | Implement business logic for budget validation. | 1
|  | Calculate budget variances. | 1
| Generate Financial Reports | Frontend Tasks | 6
|  | Generate various financial reports (trial balance, income statement, balance sheet, cash flow). | 4
|  | Customize report parameters (date range, account filters). | 2
|  | Backend Tasks | 5
|  | Create API endpoints for generating financial reports. | 2
|  | Implement report generation logic based on account balances and transactions. | 3
| Manage Currencies and Exchange Rates | Frontend Tasks | 2
|  | Manage a list of currencies with exchange rates. | 1
|  | Apply exchange rates to transactions. | 1
|  | Backend Tasks | 2
|  | Create API endpoints for managing currencies and exchange rates. | 1
|  | Implement currency conversion logic for transactions. | 1
| Audit System Changes | Frontend Tasks | 1
|  | View audit logs for different tables and records. | 1
|  | Backend Tasks | 3.5
|  | Create API endpoints for retrieving audit logs. | 1
|  | Implement audit log creation for database changes. | 0.5
Reporting Analytics | Manage Different Reports | Frontend Tasks | 5
|  | Create form to generate different reports | 2
|  | Create a list to display all reports with details. | 1
|  | Implement search and filter functionalities for reporting. | 1
|  | Implement edit and delete functionalities for reports. | 1
|  | Backend Tasks | 3
|  | Create API endpoints for adding, updating, deleting, and retrieving reportd=s. | 3